## Slide 1
FINAL DEFENSE
Smart Study Planner
A personal academic planner
with course-level collaboration hubs.
Team: StudyHub
Mahmod Khshan
lead developer
Islam Baloom
Scrum Master
Abd Al Majid Ajmil
Product Owner
Amir Arabi
Full-Stack Developer
Mustafa Sbetan
QA & DevOps Lead
Software Project Management · Spring 2026

## Slide 2
02 — The Problem
StudyHub · Smart Study Planner · Spring 2026
3 in 5
students use WhatsApp
or Telegram for course
discussion & file sharing
— yet find it inadequate.
1.
Fragmented Deadlines
Calendar apps hold deadlines, but know nothing about courses.
2.
No Separation Between Courses
Group chats mix all courses together; history gets buried.
3.
No Structured File Sharing
Cloud links shared in chats break, expire, or get lost.
4.
Zero Integration
No tool connects the planner, the chat, and the files in one place.

## Slide 3
03 — Our Solution
StudyHub · Smart Study Planner · Spring 2026
01
Personal Dashboard
Assignments & exams sorted by deadline, across all courses in one view.
02
Course Groups
Create a course with course_id + join_code. Teammates join instantly.
03
Community Hub
Chat · Materials (PDF upload) · Q&A · Activity Feed — per course.
bejewelled-valkyrie-fee7bb.netlify.app

## Slide 4
04 — Architecture
StudyHub · Smart Study Planner · Spring 2026
FRONTEND
Netlify · index.html · Vanilla JavaScript
▼
HTTPS · Fetch API
BACKEND
Render · Python Flask REST API (35 routes) · is_course_member() guard
▼
PyMongo
DATABASE
MongoDB Atlas (10 collections) + GridFS (binary file storage)
All Course Hub routes call is_course_member(course_id, username) before returning or modifying any hub data.

## Slide 5
StudyHub · Smart Study Planner · Spring 2026
Live Demo
1
Login or register with a username and password
2
Select institution and degree to discover course groups
3
Join an existing course by join_code or create a new course group
4
Add an assignment or exam — see it appear on the dashboard
5
Open the Course Hub — post a message, upload a file, ask a Q&A question
https://bejewelled-valkyrie-fee7bb.netlify.app/

## Slide 6
06 — Sprint Journey & Velocity
StudyHub · Smart Study Planner · Spring 2026
Chart: Sprint Velocity (Story Points)
| Sprint 1 | Sprint 2 | Sprint 3
Story Points | 20 | 35 | 40
Sprint 1 — 20 SP
Below plan (target 25). Setup overhead: Atlas IP config, first Render deploy.
Sprint 2 — 35 SP
Above plan (target 32). Team rhythm established; MVP features well-understood.
Sprint 3 — 40 SP
On trend. Integration overhead limited further acceleration compared with Sprint 2.
Avg velocity: 31.7 SP/sprint · Sprint 3 delivery stayed close to the expected range based on Sprint 2 velocity.

## Slide 7
07 — Final EVM Scorecard
StudyHub · Smart Study Planner · Spring 2026
0.95
SPI
(Schedule Performance)
0.81
CPI
(Cost Performance)
95%
Scope Delivered
(of 100 planned SP)
−24h
VAC
(Cost Variance at Completion)
Chart: 
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3
PV (Planned) | 0 | 25 | 57 | 100
EV (Earned) | 0 | 20 | 55 | 95
We stayed close to schedule and delivered most planned scope — but underestimated integration cost (CPI 0.81).

## Slide 8
08 — Risks That Materialized
StudyHub · Smart Study Planner · Spring 2026
R-03
Course Privacy — Missing Membership Check
Trigger: Hub GET routes initially returned data for any course_id without verifying the requester was a member.
Action: Added is_course_member() guard to every hub route. All hub data is now membership-gated.
Verdict: Ineffective contingency — risk was not identified in advance. Fix cost ~8 hrs to trace.
R-04
GridFS Learning Curve
Trigger: File upload, download, and cascade delete took 16 hrs vs. 4 hrs estimated.
Action: Absorbed via overtime. No contingency had been planned for a new storage library.
Verdict: Ineffective — treated as simple CRUD. Should have been a dedicated spike.

## Slide 9
09 — Lessons Learned
StudyHub · Smart Study Planner · Spring 2026
01
Estimation
New infrastructure needs a spike first.
GridFS was treated as a simple library call and estimated at 4 hrs. It took 16. Any new storage or auth model must be spiked before sprint planning — estimate at 3× the spike findings.
02
Process
Authorization must be part of Definition of Done.
Authentication (who are you?) and authorization (are you allowed?) are separate layers. Every hub route needs an explicit membership check in its DoD checklist — not discovered during integration testing.
03
Demo Readiness
Test from a cold deployment, not a warm one.
Render's free tier spins down after 15 minutes. The cold-start 502 appeared during rehearsal, not during development. Run a full Golden Path from cold at least 24 hrs before the defense.

## Slide 10
StudyHub · Smart Study Planner · Spring 2026
What's Next
>>
Deferred
Mobile-Responsive Layout (US-22)
The highest-value next sprint. Most academic task management happens on a phone — the current desktop layout requires horizontal scrolling.
>>
Known Gap
Hub Moderation Workflow
Flag mechanism exists in hub_reports. Owner-facing review UI and hide/remove actions are not yet built.
>>
Known Gap
Server-Side Session Management
Current session uses browser storage. A production deployment requires server-side token validation or JWT-based authentication.
Thank you. Questions?
StudyHub · Smart Study Planner · Spring 2026 · Software Project Management